## Sheet1
|  | Wk1 |  |  |  | Wk2 | [6 empty] | Wk3 | [6 empty] | Wk4 | [6 empty] | Wk5 | [6 empty] | Wk6 | [6 empty] | Wk7 | [6 empty] | Wk8 | [6 empty] | Wk9 | [6 empty] | Wk10 | [6 empty] | Wk11
 | time axis 2014-04-09 to 2014-06-20
Portfolio Content |  | 2014-04-29: 50%; 2014-05-20: 100%
| Guardians | 2014-05-20: final tweaks
Multi object js | bar: 2014-04-20 to 2014-04-29; 2014-05-20 to 2014-05-21
News articles PHP | bar: 2014-04-30 to 2014-05-08; 2014-05-20 to 2014-05-21
AW site | bar: 2014-05-09 to 2014-05-18; 2014-05-20 to 2014-05-21
| Portfolio Site | 2014-04-09: Organize Content; 2014-04-15: Research for inspiration; 2014-04-26: Mockups; 2014-05-06: Style guide & Paper prototypes?; 2014-05-11: Site build; 2014-05-27: critique!; 2014-05-28: site build/fix found issues + written content & forms; 2014-06-03: critique; 2014-06-10: Completed site due; 2014-06-12: FINAL site files + all assignments due by 7:45P
Assignments W1D1 | bar: 2014-04-09 to 2014-04-10
| Organize and Assess Portfolio Content | 2014-04-09: W1D2
| Milestones & Gantt Chart Timeline | 2014-04-09: W1D2
| Hosting and URL | 2014-04-09: W1D2
| Basic Splash Page set up | 2014-04-09: W1D2
| Subdomain Set up | 2014-04-09: W1D2
| Video: Building a Brand | 2014-04-09: W1D2
Assignments W1D2 | bar: 2014-04-09 to 2014-04-15
| Job Market List | 2014-04-11: W2D1
| 30 second call ( Due: before 8am Tues. ) | 2014-04-14: By 8AM Tues
| Mind Mapping | 2014-04-10: W2D1
| Research portfolio sites for inspiration | 2014-04-15: W3D1; 2014-04-22: due
Email mentors | bar: 2014-04-14
Assignments W2D1 | bar: 2014-04-09 to 2014-04-17
| Proposal | 2014-04-15: W2D2
| Estimate | 2014-04-15: W2D2
| Target Audience | 2014-04-16: W2D2
| Content Strategy | 2014-04-16: W2D2
| Identity Design Sketches | 2014-04-15: W2D2
| Inspiration | 2014-04-17: W3D1; 2014-04-22: due
Assignments W2D2 | bar: 2014-04-09 to 2014-04-22
| Identity Sketches | 2014-04-18: W3D1
| Flow Charts | 2014-04-18: W3D1
| Agency Lists | 2014-04-20: W3D2
| Wireframes and Moodboards | 2014-04-21: W3D2
Readings: Ethics book | bar: 2014-04-21
Assignments W3D1 | bar: 2014-04-09 to 2014-04-24
| Agency Lists | 2014-04-22: W3D2
| Wireframes and Moodboards | 2014-04-23: W3D2
| Video: More Perfect Typography | 2014-04-22: W3D2
| Video: Most Awkward 404 page | 2014-04-22: W3D2
| Font Combinations: Headers and Body copy | 2014-04-22: W3D2
| Identity: 3 illustrator mock-ups | 2014-04-23: W3D2
Assignments W3D2 | bar: 2014-04-09 to 2014-04-29
| Grid System – Layout | 2014-04-25: W4D2; 2014-05-01: due
| Stacking Order | 2014-04-24: W4D1
| Color Palette – for website | 2014-04-26: W4D2; 2014-05-01: due
| Mock-ups of site in responsive sizes | 2014-04-26: W5D1; 2014-05-06: due
| Clean up of Logo | 2014-04-25: W4D2
Study for Ethics Test | bar: 2014-04-28
Assignments W4D1 | bar: 2014-04-09 to 2014-05-01
| Logo: Finalize Design | 2014-04-29: W4D2
| Contrast: Site Design | 2014-04-30: W5D2; 2014-05-08: due
| Fixes to Mock-up Designs | 2014-04-29: W4D2
Assignments W4D2 | bar: 2014-04-09 to 2014-05-06
| Requirements Document – begin | 2014-05-02: W5D1
| Final changes to Identity Work | 2014-05-01: W5D1
| PDF of Identity Process (Rough) | 2014-05-03: W5D1
| Business & Thank You Cards & Resume | 2014-05-05: W6D1; 2014-05-15: Business Cards Ordered; 2014-06-05: Resume & Thank You Cards ordered
| Testing: Contrast | 2014-05-05: W5D2
| Study for Ethics Test | 2014-05-06: TEST!
Assignments W5D1 | bar: 2014-04-09 to 2014-05-08
| Contrast | 2014-05-06: W5D2
| Style Guide for Site Design? | 2014-05-06: W6D1
| Paper Prototype? | 2014-05-07: W6D2
Assignments W5D2 | bar: 2014-04-09 to 2014-05-13
| Style Guide? | 2014-05-10: W6D1
| Paper Prototype? | 2014-05-08: W6D1
| Finalize site design and promotional ideas | 2014-05-11: W6D2; 2014-05-15: critique
Assignments W6D1 | bar: 2014-04-09 to 2014-05-15
| Send Business Cards to Printer | 2014-05-13: W6D2
| Testing: Color Sensitivity | 2014-05-13: W6D2
| Review Usability Testing | 2014-05-14: W6D2
Assignments W6D2 | bar: 2014-04-09 to 2014-05-20
| Behance? and Linked-in Accounts | 2014-05-15: W7D1; 2014-05-20: due
Assignments W7D1 | bar: 2014-04-09 to 2014-05-22
Assignments W7D2 | bar: 2014-04-09 to 2014-05-27
| Testing: Image Optimization | 2014-05-23: W8D1
| Prepare for Usability / Content review | 2014-05-25: W8D1
Assignments W8D1 | bar: 2014-04-09 to 2014-05-29
| Fix found issues | 2014-05-27: W9D1
| Finalize All Project Descriptions | 2014-05-27: W9D1
Assignments W8D2 | bar: 2014-04-09 to 2014-06-03
| Written Content | 2014-05-29: W9D1
| Form Functionality | 2014-05-31: W9D1
Assignments W9D1 | bar: 2014-04-09 to 2014-06-05
| Final Tweaks before Industry Review | 2014-06-03: URL sent Friday morning
| Identity System | 2014-06-03: W9D2
Assignments W9D2 | bar: 2014-04-09 to 2014-06-10
Assignments W10D1 | bar: 2014-04-09 to 2014-06-12
| Portfolio Site Finished! | 2014-06-10: due in class for Industry Speed Networking / Review
| Fix Found Issues/Suggestions by Reviewers? | 2014-06-10: Wk10D2
Assignments W10D2
| Reading: Additional Texts | 2014-06-12: W11D1
| Final Assignment | 2014-06-13: W11D1
Assignments W11
Porfolio Show! | bar: 2014-06-19
| GRADUATION!!! | 2014-06-20: !!!